## Sheet1
Action Items from the Annual NCC Meeting in Raleigh, NC, January 26-27,2011
Please refer to the appropriate section of the NCC minutes for context.
Action Item | Who Responsible | Due Date | Status | Date Completed | Comments and Updates
Tribal Relations
Carl will look at what is currently on his SharePoint site dealing with outreach on Tribal Nations. He will work with Kristian to determine if some of this material can be posted to the CAPS Resource and Collaboration Site. | Carl Etsitty, Kristian Rondeau |  | Ongoing |  | Still needs to be done.
Carl will keep the CAPS program informed of any events/meetings that may be of interest to the Program (ATNI, ATNWI, NCAI, along with other local and regional meetings). | Carl Etsitty |  | Ongoing |  | Ongoing, need to reingage Carl
John will look into developing a national outreach message and materials (e.g., a display) for CAPS that can be made available to cooperators. | John Bowers |  | Planned for FY12 FB |  | Planned suggestion for 2012 Farm Bill funding; Recently completed Stone Fruit Outreach materials
Farm Bill Update
Matt will compile a comprehensive report of progress to date. | Matt Royer |  | Ongoing |  | Continually in progress
Matt will keep the NCC up to date on the current Farm Bill situation. | Matt Royer |  | Ongoing |  | Continually in progress
CPHST-CAPS Support | (need to reconcile with CPHST action item work sheets)
Rick will develop a chart showing CPHST collaborators, what they do, etc. This will be under development for some time as CPHST determines what resources are available (this is still a fluid situation in CPHST as it responds to budget realities). In due time, this information will be shared with the CAPS community. | Rick Zink |  | Completed |  | 7/6/11: In progress and under review by Phil Berger; 2/1/12: Rick will present at NCC meeting in Miami
SSCs will discuss at the upcoming breakout sessions at the regional Plant Board meetings what support they need and how CPHST can help (this can be done regionally, so several states can request support together). | SSCs |  | ??? |  | need follow up with SSCs
NCC Bylaws
No change in the bylaws or mission statement | John Bowers |  | Completed | 2011-01-26
Change the National/Regional Survey Coordinator designation to National/Regional Program Manager ??? | Matt Royer, John Bowers |  | In progress |  | Matt to discuss with David Kaplan
Review of CAPS Conference
The NCC needs to decide if the awards recognition should be done every year or only years with CAPS Conferences. Whenever this is next organized, the NCC needs to give more clear direction on what is expected on the nomination form. | NCC |  | Ongoing |  | To be discussed at NCC meeting in Miami
During the Plant Board meeting, SPROs on the NCC should request 10-15 minutes to give a summary of the CAPS Conference. | SPROs |  | ??? |  | need follow up with SPROs
Nancy and Beth will complete a first draft on an executive summary (two page max, preferably one) of the summary report on the CAPS Conference before the end of February. | Nancy Richwine, Beth Long |  | Completed |  | 1/27/11: Submitted draft to the NCC for review
Any comments or changes to the National CAPS Conference documents should be sent to John who will compile corrections and finalize the documents. The final document will be sent out and should be used when presenting at the National Plant Boards. | NCC, John Bowers |  | Completed | 2011-02-23 | Executive Summary of Evaluations, NCC Minutes, and NCC Action Items posted on the CAPS R&C site.
John will determine how many people responded to the feedback questionnaire. | John Bowers |  | Completed | 2011-02-07 | Seventy-eight evaluation forms were received out of 209 total participants registered (37.3%).
The SCCs and PSSs (and Kristian) on the NCC should outline what is needed for “CAPS 101.” They will come up with a list of topics that are needed, and recommend content, presentation, delivery and other issues associated with informing new and not so new members of the CAPS community about the CAPS Program. | PSSs and SSCs |  | In progress |  | 3/3/11: email sent as call for volunteers to form CAPS 101 Working Group as discussed on NCC call; 2/1/12: Group will present CAPS'opedia to NCC in Miami 2/1/12
CAPS 101 should include information on how to form and operate a State CAPS Committee. | PSSs and SSCs, John Bowers, Brian Kopper, Kristian Rondeau |  | In progress |  | Topic to be discussed by CAPS 101 Working Group
John, Brian, and Kristian will look into the possibility of a TDY or developmental assignment for the purposes of beginning the development of a CAPS 101 document/website/ training module. | John Bowers, Brian Kopper, Kristian Rondeau |  | Ongoing |  | Topic to be discussed by CAPS 101 Working Group; morphed into CAPS'opedia concept for CAPS R&C site
NCC members should let John know when new people come into the program. John will include this information on the CAPS listserv and can include it in the News and Announcements portion of the CAPS R&C site. | NCC, John Bowers |  | Ongoing |  | Continually in progress
ISPM Standards and Language
Create an outreach document that states what the CAPS mission is and how it relates to the International Standards. | John Bowers |  | Ongoing |  | Still needs to be done; Need input from PIM, trade directors, and export staff
Align the language in the Survey Guidelines with the ISPMs | John Bowers, Brian Kopper, Kristian Rondeau |  | Ongoing |  | Needs review and input from PIM, trade directors, and export staff
NCC needs to determine what pest status terms will be adopted by CAPS. | NCC |  | Ongoing |  | Need input from PIM, trade directors, and export staff
2012 Survey Guidelines
Format and Presentation
NCC members should go through the CAPS documents (especially the Guidelines and appendices) and send all comments and suggestions, even small editorial changes, to John for consideration in the 2012 Guidelines. | NCC |  | Completed | 2011-04-18 | 2012 Guidelines published
Although the PDF format works well, the NCC should look into other formats and delivery options for consideration, especially as technology changes. | NCC, John Bowers |  | Ongoing |  | Continually in progress; CPHST will discuss at NCC meeting in Miami 2/1/12
John will talk to Susan to see if she can provide hit statistics on the CAPS R&C site to determine who is going on the site and what they are looking at, with specific interest in the Guidelines pages. | John Bowers, Susan Schechter |  | In progress | 2011-03-05 | Susan provided two documents with metrics for the CAPS R&C site. Needs editing before releasing to the NCC.
Commodity Documents vs Individual Pest Data Sheets | (need to reconcile with CPHST action item work sheets)
Rick and team will develop an example of the individual grouped datasheets and a separate intro document for the Asian Defoliator Survey. The Intro document will describe how to survey for Asian defoliators, a description of the pathway, reason as to why this survey is important, etc. | Rick Zink | 4/1/2012 due date for incorporation into 2013 Guidelines | Pending |  | 7/6/11: The Asian Defoliator Survey will be added to the 2013 Guidelines. -Lisa J.- 1/26/12: An update will be provided at 2012 NCC meeting. Pest list available in April, 2 example datasheets available for review in April, complete delivery by August 1st (or earlier).
The NCC will review this document and provide feedback for future “intro documents.” | NCC | " | Pending |  | These issues to be discussed at 2012 NCC meeting in Miami 2/1/12
The NCC needs a name to refer to these new documents. | NCC | " | Pending
Rick and team will develop the Intro document and grouped datasheets for palm pests. It will have a short introduction on how to survey in palms as well as individual pest sheets on pests of palm. Datasheets can be pulled from Terrence's Lucid key and revised for our needs. | Rick Zink | " | Pending |  | 7/6/11: Terrence will not have his palm resource finalized until August. Once this is complete, the CPHST group will begin work on the introduction and datasheets. Melinda has started developing a preliminary pest list.--MS 1/27/12: We are still evaluating if palm will be offered during the 2013 or 2014 survey season. There are survey/diagnostics issues for the pathogens. An update will be provided at 2012 NCC Meeting.
Rick, Terrence, and John will discuss the best way to proceed over the next year for the datasheets and determine the best way to deliver the product. | Rick Zink, John Bowers, Terrence Walters | " | Pending |  | 7/6/11: Topic to be presented and discussed in an upcoming webinar 1/27/12: Melinda/Lisa will touch on the web-based delivery option during the update to the 2012 NCC meeting. The current plan is to have two example datasheets for NCC review in April.
When updating commodity documents, Lisa will break bigger documents up into smaller parts (by chapter, intro, pest datasheets, references, etc.). | Lisa Jackson | " | Completed | 2011-07-06 | Need to discuss, other ways of navigating within a document.-- John B. 7/6/11: Group agreed it is ok not to change the old documents.--LJ
Commodity/Taxon Documents
Lisa and Melinda will prepare the Cotton and Stone Fruit Commodity Pest Lists for inclusion in the 2012 Survey Guidelines. | Lisa Jackson, Melinda Sullivan | 2011-07-06 | Completed | 2011-07-06 | 7/6/11: The Stone Fruit Reference has been posted to the CAPS website and is in an open review period until Aug.1.--Lisa J. 7/18/11: Stone Fruit Guideline document will be completed and posted for review on or before Aug. 1.--MS 1/26/12: Stone fruit reference and guidelines are posted on CAPS Resource and Collaboration site. Cotton reference was posted Dec. 13, 2011 for review. Review period will end on Feb. 7, 2012. Cotton guidelines is near completion. The survey chapter is taking longer than expected due to acreage differences between states and trapping differences in Bt vs. non-Bt crops. This should be available within a few weeks.--MS
The approved survey methodology also will be added to the CAPS-Approved Methods website for these pests. | Lisa Jackson, Melinda Sullivan | 2011-07-06 | Completed | 2011-07-06 | 7/6/11: Completed.--Lisa J.
Asian Defoliators
Lisa and Talitha will prepare the Asian Defoliator data sheets, the Intro document, and pest list for inclusion in the 2012 Survey Guidelines. | Lisa Jackson, Talitha Price | Datasheets: 4/1/2012 Intro: 6/1/2012 | In Progress |  | 1/26/12: Datasheets and approved methods will be completed by April 2012. The Introduction will be completed by June 2012.--Lisa J.
The approved survey methodology also will be added to the CAPS-Approved Methods website for these pests. | Lisa Jackson | 2012-04-01 | Completed | 2011-07-08 | 1/26/12: Survey methodology is available for the main targets. Info for new targets will not be posted until April 2012.--Lisa J.
Weeds
SPROs and SSCs to ask if weeds are important to states at the regional Plant Board meetings. Would states survey for weeds over other things (at the expense of something else)? Results will be reported back on one of the NCC conference calls. | SPROs & SSCs |  |  |  | need to follow up; discuss at 2012 NCC meeting in Miami
New Pests
When releasing the 2012 Guidelines, John will include a letter relating notable pest finds over the year that may be important to bring to the states’ attention. | John Bowers |  | Completed | 2011-04-18 | A letter detailing changes to the 2012 Survey Guidelines was included when the Guidelines were published; did not necessarily include a listing of pest finds, but instructed the states to note changes to the pest lists.
Snails
No action items, continue as in previous years |  |  | Completed | 2011-01-27
Pest List Working Group (PLWG) Recommendations
Hylurgops palliatus, Hylurgops ligniperda, and Orthotomicus erosus to continue to be included in the EWB/BB manual for 2012. | Lisa Jackson | 2011-04-01 | Completed | 2011-04-01 | 1/26/12: For 2013, the Pest List Working Group recommends removal from the EWB/BB manual and adding to the Additional Pests of Concern List.
Xylotrechus will be broken down to species level for 2012. Several species will be identified as survey targets for which negative data can be entered. | Lisa Jackson | 2011-04-01 | Completed | 2011-04-01 | 7/6/11: Simple datasheets (host info only) are being developed for 4 Xylotrechus species for the 2012 EWB/BB National Survey Guidelines. This info will be for reference purposes only. For 2012, only positive data will be accepted at the species level for any exotics that are identified (may have been caught in traps, etc.). --Lisa J. 1/26/12: The 2012 version of the EWB/BB manual will be posted soon with this new info.--LJ
Xyleborus will continue at genus level until it can be broken down to species level. | Lisa Jackson | 2011-04-01 | Completed | 2011-04-01 | 7/6/11: Xyleborus will remain at genus level for 2011 with negative data reportable from visual surveys. For 2012, only positive data will be accepted at the species level for any exotics that are identified (may have been caught in traps, etc.). Information on the genus Xyleborus is listed in the 2012 EWB/BB National Survey Guidelines for reference purposes only.--Lisa J.
Negative data for Xyleborus will not be accepted at the genus level. Positive data should be reported at the species level for any specimens that are caught in traps. This will need to be changed in the 2012 Guidelines. | John Bowers | 2011-04-01 | Completed | 2011-04-01 | Incorporated into Appendix N in 2012 Guidelines; no negative data at genus or species level
Lisa will work with Kathy and John to look at data that has already been entered for Xyleborus and recommend changes, if any. | Lisa Jackson, Kathy Handy |  | Completed | 2011-04-18
John will contact the Citrus Health Response Program (CHRP) to ask them to take over ownership and responsibility for updating the Citrus Commodity Survey documents. | John Bowers |  | Completed | 2011-09-14 | sent email to Pat Gomes & Charla Hollingsworth on 2/2/11; no response as of 2/18/11; Call w/ CHRP - transfer ownership of citrus commodity documents to program
Duponchelia fovealis will not be supported for surveys in 2012 and will be dropped from all lists. | Lisa Jackson | 2011-04-01 | Completed | 2011-04-01
Eudocima fullonia will be kept on the CAPS list for now; Lisa will talk to Steve Passoa again about ID issues. | Lisa Jackson | 2011-04-01 | Completed | 2011-04-01 | 6/24/11: Julieta Brambila is helping us with the ID portion of the datasheet.--Lisa J.
Federal Noxious Weeds
FNW will not asked to be removed from the AHP and will be supported for survey for the time being | Lisa jackson |  | Completed | 2011-01-27
Pine Commodity Pest List
Melinda will update the Pine Commodity Guidelines, pest list, and approved methods to include Mycosphaerella gibsonii and Cronartium flaccidum | Melinda Sullivan |  | Completed |  | 1/26/12: Three more 2012 insect pests were added to the Pine Reference and Guidelines. The 2012 versions should be posted by March 2012. --Lisa J.
Validation of Molecular Methods/Cyst Nematodes
CPHST will have internal discussions with Laurene Levy (Director, CPHST Beltsville Lab.) very soon to discuss options for molecular diagnostic methods and protocols for cyst nematodes. | Rick Zink |  | Completed | 2011-01-20 | 7/6/11: In progress and pending FY12 CPHSTfunding. 1/26/12: We are planning a follow-up call with Beltsville the week of Feb. 13, 2012 to discuss future R&D options and changes/priorties for Beltsville due to the re-organization of the lab (combining with MDL)-MS
Laurene will look at the literature that Melinda has pulled together and work on getting “screening” methods approved for use in the CAPS program. | Melinda Sullivan |  | Completed | 2011-01-20 | Continually in progress with discussions with CPHST Beltsville lab
Common Names for Pests
Melinda will check with Lisa and send a list to Joel for review (cc: John Bowers) (after checking ESA and APS accepted common name list). If there is agreement with NIS and CPHST, then name change will occur. Melinda/Lisa will then request changes be made to Susan. | Melinda Sullivan, Lisa Jackson, Joel Floyd |  | In progress |  | 5/24/11: Melinda sent her names to Joel Floyd. Agreement was reached on the few name changes. Lisa will need some time to work on hers.-- Melinda S. Continually in progress
AHP/Commodity Pests to be Removed?
For now, Planococcus minor should stay, but will be periodically reviewed. | Lisa Jackson | 2012-04-01 | In progress |  | 1/26/12: Under consideration for removal from the AHP list. Waiting for NPAG’s revised report. The report has been completed and is waiting for NPB’s approval. The report should be finalized by April.--LJ
Pests to Consider and Discuss by PLWG
The process for considering pests for inclusion to or deletion from a Commodity Pest List by the PLWG is to forward that pest via the NCC member for that constituency to John/Lisa/Melinda, who will add that pest to the PLWG agenda. | NCC |  | Completed | 2011-04-01 | PLWG will accept and review changes to the pest list annually
CAPS Conference Breakout Session on Pests
For the AHP list, John will investigate with CPHST the possibility and what would be involved into identifying criteria and developing weights for each taxon. | John Bowers |  | In progress |  | Met with Kim Schwartzburg 1/26/11 to discuss the AHP process
The discussion to continue on future NCC conference calls as to where the NCC would like to go with this issue. | NCC |  | In progress |  | CPHST Pest List review for pests to be included in the AHP model; pre-assessment favored as opposed to criteria with weights
AHP List
In order to maintain a program focus, the 2012 AHP list will be abbreviated to the top 54 pests (top 50 ranks). | NCC |  | Completed | 2011-01-27 | Decision by NCC
John will communicate the NCC decision to Gary Cave. | John Bowers |  | Completed | 2011-02-02 | Sent email to Gary Cave and David Prokyrm on 2/2/11; no response received as of 2/18/11
Pests that have approved methods will be clearly marked on the list | Lisa Jackson |  |  |  | 6/24/11: Do we really need to do this? They are sortable in the Approved Methods.--Lisa J.
The lower ranking pests will be moved to the Additional Pests of Concern List so that they stay on states’ radars. | Lisa Jackson | 2011-04-01 | Completed | 2011-04-01
Update Appendix D (explains AHP process) to include all pests that were submitted for CAPS consideration and have an explanation for why those that fell below the cut they did not make the list (increases transparency). Keep the host matrix for Appendix D. | Gary Cave, John Bowers, Lisa Jackson |  | ??? - was this communicated? |  | 7/6/11: I don't think this ever happened, but folks did ask for it.--Lisa J. This didn't happen to my knowledge either. Do we need to do this now? M.S.
John will talk to Dan about updating NAPPFAST with the current AHP list. | John Bowers | 2011-04-01 | Completed | 2011-04-01 | 7/6/11: I provided Dan with the 2012 Prioritized Pest Lists.--Lisa J.
Pests on the Additional Pests of Concern List will be annotated to include the source and/or reason that pest is on the list. | Lisa Jackson, Talitha Price | 2011-04-01 | Completed | 2011-04-01
How to Use the AHP List in the Future
Rick will liaise between the AHP team and John to explore new options for the model as directed by John and the NCC. | Rick Zink, John Bowers |  |  |  | 7/6/11: AHP list undergoing formal review by CAPS team; present progress at the 2012 NCC meeting in Miami
Caribbean and Pacific Rim Pest Lists
Pests on the GCSI list that are relevant and not already represented on any CAPS list should be added to the Additional Pests of Concern List. | Lisa Jackson | 2011-04-01 | Completed | 2011-04-01 | 3/24/11: Four insects and 1 mite were added to the 2012 Add'l Pests of Concern List.--LJ
Eventually these can be run through the AHP model along with the other pests on the Additional Pests of Concern List. | Lisa Jackson, Gary Cave |  | Pending |  | pending based on outcome of the AHP Pest List review
Brian and Kristian will relay these pests onto PR and HI, as well as the tropical pests that did not make the top 54 on the AHP List, to ensure that they are on their radar | Kristian Rondeau, Brian Kopper |  | Completed
Other Pest Issues
The CAPS Program will determine what diagnostics are available and whether Phytophthora can be a possible taxon survey for 2013 or later. | John Bowers, Melinda Sullivan, Lisa Jackson |  | Pending |  | 2/1/11: John would like to hold off on adding P. kernoviae until the diagnostics are better defined.--LJ 7/18/11: John wanted to hold off until we had validated species-specific primers. Right now, just using an ELISA test. I am not optimistic that we will have validated primers anytime soon--MS 1/26/12: P. kernoviae validated methods are very near completion. May need to revisit once method is available.--MS
Lisa will talk to Russ and discuss PPQ’s view on Phytophthora spp; she will report back to the NCC. | Lisa Jackson |  | Completed | 2011-07-14
J-2 Workplan and Cooperative Agreement Language
Kristian will develop a draft J-2 work plan for the NCC group to review for the 2012 guidelines. | Kristian Rondeau |  | Completed | 2011-04-18 | incorportated into 2012 Guidelines
IT Inventory and Equipment Purchases
IT equipment purchases will be put in the reporting template | Chris Pierce, Julie Van Meter |  | Completed | 2011-04-18 | Incorporated into the new Appendix P-1, Infrastructure reporting template
Brian and Kristian will look regionally to determine if equipment for the IPHIS switchover is needed. | Brian Kopper, Kristian Rondeau |  | ???
Standardized Reporting Template
Julie and Chris will provide finalized standardized reporting templates (Word document) for infrastructure and survey to John for the 2012 Survey Guidelines and for release through the CAPS R&C site. | Chris Pierce, Julie Van Meter |  | Completed | 2011-04-18 | Incorporated into the new Appendix P for the 2012 Guidelines
Julie and Chris will add a section for equipment purchases under Part A for both the infrastructure and survey template. | Chris Pierce, Julie Van Meter |  | Completed | 2011-04-18 | Incorporated into the new Appendix P for the 2012 Guidelines
Julie and Chris will complete an example for each of the templates for states to use (can be completed after March) | Chris Pierce, Julie Van Meter |  | Completed | 2011-04-18 | Incorporated into the new Appendix P for the 2012 Guidelines
Julie and Chris will change the language on IPHIS under survey and instead reference “database submission”. Also CAPS funding should read “Pest Detection”. | Chris Pierce, Julie Van Meter |  | Completed | 2011-04-18 | Incorporated into the new Appendix P for the 2012 Guidelines
Cerceris Wasp as a Survey Method
Lisa will work with Nicole on developing a protocol to be included under the approved methods section. | Lisa Jackson, Nichole Carrier | 2012-05-01 | In progress |  | 1/26/12: Cerceris wasps were recently added as an approved method for 2012. The method is approved for A. biguttatus and A. coxalis but not for EAB. Nichole and Lisa have a working draft of a Cerceris protocol and will complete it in the next few months.--LJ
IPHIS and Data Management
John, Brian, and Kristian will craft general language for the guidelines referring to data management to be updated in early summer until the NCC gets a feel for what needs to go there. ISIS information will be removed, and IPHIS language will be included for 2012. A draft will be completed and sent out for review. The guidelines will be updated as information is gathered. | John Bowers, Brian Kopper, Kristian Rondeau |  | Completed | 2011-04-18 | transition to IPHIS is in progress, abiet slowly. CAPS will use NAPIS in 2012
Outreach
NCC should inquire of their constituency if the is a need for CAPS-related outreach material that can be developed at the national level for use in the states (similar to the stone fruit outreach project), and what that outreach effort should be. | NCC |  | ongoing |  | possible Farm Bill suggestion for FY12
Toolbox for Survey Planning
At the regional Plant Board Meetings, the SSCs should discuss with others what tools they would like to have developed, what needs should be met with these tools, and if they are using/know about current tools. | SSCs |  | ???
Lisa will try to obtain the PERAL excel sheet containing websites for different taxonomic groups to distribute as a tool for state use. | Lisa Jackson |  | Completed | 2011-06-01
States that would like Brian, Kristian, or John to attend their state CAPS Committee meeting should inform them. This will be a good way for them to answer questions that come up regarding the state committees and planning for surveys. | NCC |  | not possible this year |  | Travel restrictions preclude extra travel
Molecular Diagnostic Assessment Team (MDAT)
If there are any molecular diagnostics needed that deal with insects, states should inform John, who will submit the project to MDAT. | NCC |  | Ongoing |  | Suggestion from Nancy: Silver Y Moth; suggestion from Lisa: Adoxophyas orana.
John will put minutes from MDAT conference calls in the NCC folder on the CAPS R&C site | John Bowers |  | pending |  | MDAT slow moving, will use Decision Lens and develop criteria to evaluate needs; conference call notes not always distributed
Status
Not Started
In Progress
Ongoing
Completed